## Tabelle1
Porting to new ModelView – Problems

Issue	Fixed	Notes
„Block selection mode“ :-)	x
Album Refresh (F5) not working	x
batchtools disabled in Tools menu	x
Click on thumb for preview, change imagetype filter, image is gone and navigation is greyed out	x	not reproducible for me (Marcel) / I can always confirm this (maybe Qt 4.5.1 related?) (Andi)
Clicking on the thumbnail in the thumbbar	x
Context menu is only partial visible on first click	x
Copy / paste not working	x
D&D crashes digiKam sometimes (not in all albums)	x
Deleted images still visible	x
Disabled navigation in bottom right corner	x	when? (Marcel) / When entering a new album (Andi)
Edit button not always working	x
Filtered view not updated	x	Go into a folder, select some filter (star rating), remove the rating from some of the filtered items => they will be still visible. (Andi)
First item of each album in recursive mode is offset (appears in the previous album)	x
Flickering	x
mark thumb in iconview (no preview), collapse panel, selected thumbs moves around in a wrong way (sometimes out of the window)	x
Metadata update when navigating pictures is slower than before	x
MS: Compilation is broken under Vista using MinGW	x
MS: spacing problems between icon items	x
Navigation by keyboard shortcuts	x
Navigation by SHIFT+Arrow keys is broken	x
Quickfilter text search not working correctly (search for tags is broken)	x
Rating is broken (by menu / sidebar)	x
Rating is broken (by shortcuts)	x
Rating is broken (over icon view item)	x
Right-clicking on another item doesn't deselect the previous selected item	x
Set recursive view mode only effected by restart	x
Slow creation of context menu	x
StatusLED not updated correctly when filtering in recursive album view		click on the parent folder and, although matches are found, the LED stays red. Maybe process() is called too often (race condition)? / Andi
Tag / album counters not always updated		sorry, not working for me. / To test: go into tag view. Remove images (to trash so you can restore them). Counter is not updated, only after restart. / When adding images / restoring them from trash), counter is updated / (Andi)
Thumbnail rotation does not change.	x	when? (Marcel) / Always. Rotate an image with the overlay icons, the image gets rotated, the thumb is not. (Andi)