## Tabelle1
Porting to new ModelView – Problems

Issue	Fixed	Notes
„Block selection mode“ :-)	x
Album Refresh (F5) not working
batchtools disabled in Tools menu	x
Click on thumb for preview, change imagetype filter, image is gone and navigation is greyed out		not reproducible for me (Marcel) / I can always confirm this (maybe Qt 4.5.1 related?) (Andi)
Clicking on the thumbnail in the thumbbar	x
Context menu is only partial visible on first click	x
Copy / paste not working
D&D crashes digiKam sometimes (not in all albums)	x
Deleted images still visible	x
Disabled navigation in bottom right corner		when? (Marcel) / When entering a new album (Andi)
Edit button not always working	x
First item of each album in recursive mode is offset (appears in the previous album)	x
Flickering	x
mark thumb in iconview (no preview), collapse panel, selected thumbs moves around in a wrong way (sometimes out of the window)	x
Metadata update when navigating pictures is slower than before	x
MS: Compilation is broken under Vista using MinGW	x
MS: spacing problems between icon items	x
Navigation by keyboard shortcuts	x
Navigation by SHIFT+Arrow keys is broken	x
Quickfilter text search not working correctly (search for tags is broken)	x
Rating is broken (by menu / sidebar)
Rating is broken (by shortcuts)
Rating is broken (over icon view item)
Right-clicking on another item doesn't deselect the previous selected item	x
Set recursive view mode only effected by restart	x
Slow creation of context menu	(x)	Fixed for me – Andi
Tag / album counters not always updated
Thumbnail rotation does not change.		when?